Project Proposal: Digitization of Archival Collections

Bonnie McLane

School of Information, University of South Florida

LIS 6409: Introduction to Library Administration

Dr. Barbara Stites

November 29, 2023

PROBLEM

Several of the more popular archival collections that patrons request when they make a reading room appointment contain materials that have been damaged by repeated handling or simply have degraded over time due to the fragility of the materials and will not survive being physically handled for much longer.

SOLUTION

Digitization of these popular yet fragile collections so patrons can still access them online while the materials are taken out of physical usage by the public for purposes of preservation.

REQUIRED RESOURCES

Staffing: The Archives and Special Collections department of the library will need to hire a digital curator to oversee the project. Up to three student assistants from within Special Collections will assist with the project as their main assignment when not staffing the Reading Room.

Equipment: Special Collections will collaborate with Digital Humanities to arrange the use of the scanning and image capture technologies in the DH lab.

Training: The student assistants will need to be trained to create metadata for the selected collections both before and after the digitization process if they do not have prior experience with creating metadata from working at Special Collections, as well as how to perform a quality control review of the digitized materials. Their work will be reviewed by the Special Collections Cataloging/Metadata team for accuracy and adherence to metadata standards. The actual digitization and image processing will be taken care of by Digital Humanities student employees already familiar with the scanning/image capture technologies in the DH lab, although it will be useful for the digital curator and any Special Collections employees who might be involved in future digitization projects to familiarize themselves with using these technologies. Both the digital curator and the student assistants will have to familiarize themselves with the digital repository software Special Collections uses to house their digitized materials.

PROJECT PARTNERS

Digital Humanities

Human Resources

Preservation

Metadata (unit within Collections & Discovery)

BRIEF ASSESSMENT PLAN

Success will be measured by the number of views (e.g., daily, monthly, yearly) of digitized materials accessible through institutional repository dedicated to digitized archival materials in Special Collections, which may be tracked live on the website through GIS software (like Google Earth/Google Maps) in addition to regular means of aggregating average page views to give Special Collections an idea of the global reach/impact of our collections. The annual number of views/downloads per collection will be compared to the annual number of requests per collection prior to digitization.

BUDGET

| Salaries | Expenses | Comments |
| --- | --- | --- |
| Digital curator 1.0 FTE | 62,400 | $30/hr, 2,080 hours |
| Student Assistant 0.5 FTE | 7,800 | Not benefit-earning; $15/hr, 520 hours |
| Student Assistant 0.5 FTE | 7,800 | Not benefit earning; $15/hr, 520 hours |
| Student Assistant 0.5 FTE | 7,800 | Not benefit-earning; $15/hr, 520 hours |
| Benefits | Expenses | Comments |
| Digital curator 1.0 FTE | 18,000 | 30% benefits |
| Student Assistant 0.5 FTE | 597 | 7.65% benefits |
| Student Assistant 0.5 FTE | 597 | 7.65% benefits |
| Student Assistant 0.5 FTE | 597 | 7.65% benefits |

TIMELINE

| Due Date | Activity |
| --- | --- |
| January 1, 20xx | Get dean’s approval for proposal. |
| January 15, 20xx | Identify and reach out to stakeholders—students, faculty, other past and/or potential patrons—as well as Digital Humanities, Human Resources, other potential partners within the library. |
| January 15, 20xx | Draft and publish job opening for digital curator position. |
| February 15, 20xx | Begin reviewing applications for digital curator position. |
| April 15, 20xx | Digital curator hired, onboarded. |
| May 15, 20xx | Complete appraisal of existing archival collections to identify which collections are most in need of digitization and narrow down to top three for pilot project. |
| May 20, 20xx | Initial project meeting with Digital Humanities, Human Resources department heads, Special Collections Cataloging team, and library budget director to discuss project plan, including timeline and staffing/equipment needs. |
| June 1, 20xx | Submit completed project timeline, comprehensive budget to Associate Dean. |
| July 1, 20xx | Completion of metadata creation for collections to be digitized. |
| July 7, 20xx | Revision of metadata (if necessary) after review by Metadata team. |
| August 1, 20xx | Communicate with employees and project partners on project status. |
| September 1, 20xx | Completion of conservation review, including treatment of especially fragile materials. |
| September 5, 20xx | Collections receive final approval for digitization. |
| December 5, 20xx | Completion of actual digitization phase. |
| January 15, 20xx | Upload processed content to begin quality control phase. |
| March 15, 20xx | Once quality control activities are completed, package digitized content for data ingestion into digital repository. |
| April 1, 20xx | Metadata team review ingestion task, publish the collection. |
| April 1, 20xx | Library, stakeholders notified that digitized materials have been published and are available for viewing. |